Publication Roadmap v2.0

ArgusVision PhD Program, Panagiotis Fragkos

PhD in Photogrammetry, NTUA. Supervisor Prof. Charalampos Ioannidis. July 2026.

# 1. Purpose and Strategy Change

This roadmap turns the Master thesis material (Phase 0 of the ArgusVision program) into a publication sequence for the first two years of the PhD. It replaces the July 2026 draft, which planned four journal papers opening with a standalone VBB versus OBB letter.

The letter was cancelled for a specific reason. It compared COCO-pretrained VBB models against DOTA-pretrained OBB models, and that comparison confounds bounding box representation with training domain. A reviewer would spot it on first read. The material is stronger inside the flagship paper, where a new ablation (VBB models trained on DOTA HBB annotations) resolves the confound directly.

Two more changes. Scientific Data was dropped as the dataset venue because its review times of four to eight months defeat the goal of a fast first acceptance. A peer-reviewed conference paper was added as insurance and visibility, since conference-to-journal extension is accepted practice in the remote sensing field.

The NTUA regulation requires at least three peer-reviewed publications to defend. Conference papers and data descriptors both count. This plan produces four countable items, and the third acceptance is expected by late 2027, leaving Years 3 to 5 free of publication pressure for system building.

# 2. Overview

| # | Paper | Type | Target Venue | IF (2024) | Submit | Expected Acceptance |
| --- | --- | --- | --- | --- | --- | --- |
| P0 | AerialFuseCV Zenodo release | Data release (DOI) | Zenodo | n/a | Aug 2026 | DOI live immediately |
| P1 | AerialFuseCV data descriptor | Data descriptor | ISPRS Open Journal of P&RS | 7.0 | Sep 2026 | Nov to Dec 2026 |
| P2 | Training-free detection to segmentation (flagship) | Full journal paper | ISPRS Journal of P&RS | 12.9 | Feb 2027 | Late 2027 |
| P3 | Condensed pipeline findings | Conference paper | EarthVision (CVPR workshop) or IGARSS | n/a | Nov 2026 or Jan 2027 | Spring 2027 |
| P4 | ArgusVision full benchmark | Benchmark paper | IEEE TGRS | 9.4 | Sep to Oct 2027 | 2028 |

Table 1. Publication sequence overview.

# 3. P0, AerialFuseCV Zenodo Release (prerequisite)

DOTA v1.0 and iSAID are released for academic use and their images cannot be redistributed. The release therefore contains annotations, pairing metadata and a construction script that rebuilds AerialFuseCV from the official DOTA and iSAID downloads, with verification checksums. This is standard practice in the DOTA ecosystem. Our contribution is licensed CC-BY 4.0. The DOI becomes the citation anchor for every subsequent paper regardless of review status, which is why this step comes first and blocks everything else.

| Task | Effort |
| --- | --- |
| Package annotations and pairing metadata | 2 days |
| Construction script with verification checksums | 2 to 3 days |
| README with file structure, formats and usage | 1 day |
| Zenodo upload and DOI minting | 1 day |
| Total | about 1 week |

Table 2. P0 work items.

# 4. P1, AerialFuseCV Data Descriptor

First paired dataset reconciling DOTA v1.0 oriented bounding box annotations with iSAID instance masks at instance level. 1857 images (1401 train, 456 validation), 125102 bbox to mask pairs, 15 classes, 97.9% overall match rate. All statistics verified against the dataset analysis reports. The descriptor runs about 3000 words and requires no new experiments, which makes it the fastest paper in the portfolio and the continuity anchor the supervisor asked for.

| Priority | Venue | IF (2024) | Reasoning |
| --- | --- | --- | --- |
| Primary | ISPRS Open Journal of Photogrammetry and Remote Sensing | 7.0 | Community venue, recognized by the committee, fast review |
| Fallback | Data in Brief (Elsevier) | 1.9 | Fast and near-certain if methodology is sound |

Table 3. P1 target venues.

| Task | Effort |
| --- | --- |
| P0 complete (blocking dependency) | see Table 2 |
| End-to-end reproducibility run of the construction pipeline | 3 to 5 days |
| Write descriptor (Background, Methods, Validation, Usage Notes) | 4 to 5 days |
| Total | about 2 weeks after P0 |

Table 4. P1 extra work needed.

# 5. P2, Flagship Paper

Working title: Training-Free Detection to Segmentation for Aerial Imagery. One paper carrying the full thesis arc. Which detector representations work at all on aerial imagery, how SAM variants respond to prompt design, what the integrated YOLO to SAM pipeline achieves without any training, and where it stands against supervised end-to-end baselines. This is the paper people will cite from the thesis work, so it gets the extra experiments.

## 5.1 Material already complete from the thesis

The VBB zero-shot benchmark covers 24 COCO-pretrained YOLO models (v8 to v12) with a best F1 of 0.34%. The OBB benchmark covers 10 DOTA-pretrained models with YOLOv11x-OBB selected as backbone at 62.4% F1 and 82.8% precision. The SAM benchmark covers six configurations (ViT-H, ViT-L, ViT-B, each with box and point prompts) driven by ground truth prompts. The integrated pipeline (YOLOv11x-OBB feeding SAM-ViT-B with box prompts) reaches segmentation IoU 0.679 on matched pairs, with full timing decomposition and error propagation analysis.

## 5.2 New experiments

| Experiment | Purpose | Effort |
| --- | --- | --- |
| VBB YOLO trained on DOTA HBB annotations (2 to 3 models) | Resolves the representation versus domain confound. Core new contribution | 1 to 2 weeks |
| Mask R-CNN trained on AerialFuseCV | Supervised classic baseline | 3 to 5 days |
| YOLOv11-seg trained on AerialFuseCV | Supervised baseline in the same family as the detector | 2 to 3 days |
| Confidence-based segmentation filtering | Addresses the 18.5% false-positive overhead | 2 to 3 days |
| PR curves at IoU 0.1, 0.3 and 0.5 | Sensitivity analysis, post-hoc on existing predictions | 2 to 3 days |
| Mask2Former baseline (optional) | Modern supervised reference, only if schedule allows | 5 to 7 days |
| Total |  | about 5 to 6 weeks, parallelizable |

Table 5. P2 new experiments.

RT-DETR-seg was dropped from the baseline set. It had the weakest effort-to-value ratio of the original list.

| Priority | Venue | IF (2024) | Reasoning |
| --- | --- | --- | --- |
| Primary | ISPRS Journal of Photogrammetry and Remote Sensing | 10.6 | Exact scope fit. High desk-reject bar, expect major revisions |
| Fallback | IEEE Transactions on Geoscience and Remote Sensing | 7.5 | Broad remote sensing and aerial perception |

Table 6. P2 target venues.

# 6. P3, Conference Paper

A condensed version of the zero-shot pipeline findings, written in one to two weeks from P2 material. It serves two purposes. It is insurance, since it is the fastest-reviewing countable item in the plan and covers the case where a journal submission goes sideways. And it buys visibility and networking in the first PhD year, which for a first-year student is worth more than the paper itself. Deadlines below are approximate and must be verified when the calls open.

| Priority | Venue | Deadline (approx.) | Reasoning |
| --- | --- | --- | --- |
| Primary | EarthVision workshop at CVPR 2027 | Nov 2026 | Aerial and satellite computer vision audience, high visibility |
| Alternative | IGARSS 2027 | Jan 2027 | Large remote sensing community venue |

Table 7. P3 target venues.

# 7. P4, ArgusVision Full Benchmark

The full configuration space reserved for the PhD phase. SAM2 variants, lightweight SAM variants, a fine-tuned SAM on aerial data, hybrid and automatic prompt strategies, the complete supervised baseline set and cross-dataset validation on DIOR and NWPU VHR-10. Decision recorded here so it does not get relitigated: the benchmark goes to TGRS, not to CVPR or ICCV. Benchmark papers face brutal odds at vision conferences and a rejection there would eat four months of Year 1. A TGRS paper citing our own dataset DOI and our own flagship is the stronger outcome.

| Block | Content | Effort |
| --- | --- | --- |
| SAM2 family | tiny, small, base+, large, each with box and point prompts (8 configs) | 3 to 4 weeks including lightweight variants |
| Lightweight variants | MobileSAM, FastSAM, EfficientSAM with box and point prompts (6 configs) | included above |
| Fine-tuned SAM ViT-B on AerialFuseCV | Domain adaptation, GPU intensive | 4 to 6 weeks |
| Prompt strategies | Hybrid (box plus point) and automatic per-class selection | 2 to 3 weeks |
| Cross-dataset validation | DIOR and NWPU VHR-10 | 2 to 3 weeks |
| Writing and review cycles |  | 6 to 8 weeks |
| Total |  | about 4 to 5 months active work |

Table 8. P4 experiment blocks.

| Priority | Venue | IF (2024) | Reasoning |
| --- | --- | --- | --- |
| Primary | IEEE Transactions on Geoscience and Remote Sensing | 7.5 | Systematic benchmarks, realistic target |
| Stretch | ISPRS Journal of Photogrammetry and Remote Sensing | 10.6 | Only if findings prove landmark level |

Table 9. P4 target venues.

# 8. Timeline and Regulation Tracking

| When | Action |
| --- | --- |
| Aug 2026 | P0 Zenodo release, DOI live |
| Sep 2026 | P1 submitted (ISPRS Open Journal). P2 experiments begin |
| Nov 2026 | P1 expected acceptance. P3 EarthVision submission if the call fits |
| Dec 2026 | P2 experiments complete |
| Jan 2027 | P2 writing. P3 IGARSS submission as alternative |
| Feb 2027 | P2 submitted (ISPRS Journal) |
| Spring 2027 | P3 expected acceptance |
| Mar 2027 | P4 experiments begin |
| Sep to Oct 2027 | P4 submitted (TGRS) |
| Late 2027 | P2 expected acceptance after revisions |
| 2028 | P4 expected acceptance |

Table 10. Timeline of submissions and expected decisions.

The regulation counts acceptances, not submissions. The tracking below is the honest version of the schedule and it is the number that matters for the defense.

| Milestone | Expected | Cumulative count |
| --- | --- | --- |
| P1 accepted | Nov to Dec 2026 | 1 |
| P3 accepted | Spring 2027 | 2 |
| P2 accepted | Late 2027 | 3, requirement met |
| P4 accepted | 2028 | 4, slack |

Table 11. Progress against the three-paper regulation.

# 9. Key Dependencies

| Dependency | Blocks |
| --- | --- |
| P0 Zenodo DOI | P1 submission and citations in P2, P3, P4 |
| VBB-on-DOTA ablation | P2 core claim |
| P2 material complete | P3 condensation |
| DIOR and NWPU VHR-10 setup | P4 cross-dataset block |

Table 12. Dependency chain.

# 10. Tooling

Writing runs through WTF-P via Claude Code for all papers. Experiments use Python, PyTorch, Ultralytics, the official SAM and SAM2 repositories and Detectron2 or MMDetection for the supervised baselines. Dataset hosting on Zenodo. All experiments run on the RTX 3090 Ti.

This is a living document. It gets updated after each submission and after every major experimental decision.