Publication Roadmap

# P1, AerialFuseCV Data Descriptor

| Priority | Venue | IF | Reasoning |
| --- | --- | --- | --- |
| Primary | ISPRS Open Journal of Photogrammetry and Remote Sensing | 7.0 | Community venue, recognized by the committee, fast review |
| Fallback | Data in Brief (Elsevier) | 1.9 | Fast and near-certain if methodology is sound |

# P2, Trainig free detection to segmentation (Flagship Paper)

| Priority | Venue | IF | Reasoning |
| --- | --- | --- | --- |
| Primary | ISPRS Journal of Photogrammetry and Remote Sensing | 10.6 | Exact scope fit. High desk-reject bar, expect major revisions |
| Fallback | IEEE Transactions on Geoscience and Remote Sensing | 7.5 | Broad remote sensing and aerial perception |

# P3, Condensed pipeline findings (Conference Paper)

| Priority | Venue | Deadline (approx.) | Reasoning |
| --- | --- | --- | --- |
| Primary | EarthVision workshop at CVPR 2027 | Nov 2026 | Aerial and satellite computer vision audience, high visibility |
| Alternative | IGARSS 2027 | Jan 2027 | Large remote sensing community venue |

# P4, ArgusVision Full Benchmark

| Priority | Venue | IF | Reasoning |
| --- | --- | --- | --- |
| Primary | IEEE Transactions on Geoscience and Remote Sensing | 7.5 | Systematic benchmarks, realistic target |
| Stretch | ISPRS Journal of Photogrammetry and Remote Sensing | 10.6 | Only if findings prove landmark level |

# Timeline and Regulation Tracking

| When | Action |
| --- | --- |
| Aug 2026 | P0 Zenodo release, DOI live |
| Sep 2026 | P1 submitted (ISPRS Open Journal). P2 experiments begin |
| Nov 2026 | P1 expected acceptance. P3 EarthVision submission if the call fits |
| Dec 2026 | P2 experiments complete |
| Jan 2027 | P2 writing. P3 IGARSS submission as alternative |
| Feb 2027 | P2 submitted (ISPRS Journal) |
| Spring 2027 | P3 expected acceptance |
| Mar 2027 | P4 experiments begin |
| Sep to Oct 2027 | P4 submitted (TGRS) |
| Late 2027 | P2 expected acceptance after revisions |
| 2028 | P4 expected acceptance |